Neyece Product Build Plan Phased Sprint Roadmap · AI-Assisted Solo Development · 2026

# Overview

Neyece is a warm, playful local discovery app that replaces generic search results with vibe-matched recommendations. This document breaks the full build into five phases — each designed for solo development accelerated by AI tools like Claude Code and Cursor.

The goal is to move fast, validate early, and build the defensible moat (vibe data + Neyece Score) before competitors can catch up.

| Validate Fast Ship the waitlist first. Let real signups tell you what to build. | Build the Moat Vibe data + Neyece Score = defensible. Prioritize these above features. | AI-First Workflow Claude Code + Cursor handles scaffolding. You focus on product decisions. |
| --- | --- | --- |

# Tech Stack

Chosen for solo-founder velocity, AI tooling compatibility, and proven scalability.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js 14 + TypeScript | App router, SSR, mobile-first UI |
| Styling | Tailwind CSS | Rapid UI with brand tokens |
| Backend | Next.js API Routes + Node.js | Serverless functions, clean API layer |
| Database | PostgreSQL (Supabase) | Venue data, user profiles, vibe scores |
| Auth | Clerk | Drop-in auth, social login, user mgmt |
| AI / ML | Anthropic API (Claude) | Vibe matching, AI insight generation |
| Venue Data | Google Places API + Foursquare | Seed venue database, real-time data |
| Payments | Stripe | Future monetization, venue partnerships |
| Hosting | Vercel | Zero-config deploys, edge network |
| Storage | Supabase Storage | Venue images, user avatars |
| Analytics | PostHog | User behavior, funnel tracking |
| AI Dev Tools | Claude Code + Cursor | Code generation, refactoring, scaffolding |

# Roadmap at a Glance

| Phase | Name | What Gets Built | Duration |
| --- | --- | --- | --- |
| 0 | Foundation | Repo, DB schema, CI/CD, landing page live | 1–2 weeks |
| 1 | MVP Core | Onboarding quiz, venue feed, basic matching | 4–5 weeks |
| 2 | Intelligence | Neyece Score engine, AI insights, vibe data | 3–4 weeks |
| 3 | Social Layer | User profiles, saved spots, share cards | 3–4 weeks |
| 4 | Launch | QA, performance, waitlist onboarding, go live | 2–3 weeks |

Phase 0 Foundation · 1–2 Weeks Everything you need before writing a single line of product code.

## Sprints

| Sprint | Name | Key Deliverables | AI Tool Tip |
| --- | --- | --- | --- |
| S0.1 | Project Setup Days 1–3 | - GitHub repo with monorepo structure - Next.js 14 + TypeScript scaffolded - Tailwind configured with Neyece brand tokens (coral, yellow, cream) - Supabase project + PostgreSQL connection - Vercel deployment pipeline live - Environment variables + secrets management | Prompt Claude Code: "Scaffold a Next.js 14 monorepo with Supabase, Clerk auth, and Tailwind. Use TypeScript strictly." |
| S0.2 | Landing Page Live Days 4–7 | - HTML landing page converted to Next.js component - Waitlist email capture wired to Supabase - Eye-gradient Neyece wordmark as reusable component - Domain live (neyece.com) - Basic analytics (PostHog) installed - Share to social working | Ask Cursor to convert the HTML mockup to React components, then Claude Code to wire up the Supabase insert for emails. |

## Database Schema (Phase 0)

Define these tables before building anything else. Schema changes are expensive later.

- users — id, email, name, city, created_at, vibe_profile (JSONB)

- venues — id, name, neighborhood, city, lat, lng, category, google_place_id, vibe_tags (JSONB)

- vibe_profiles — user_id, answers (JSONB), fingerprint_vector, updated_at

- neyece_scores — venue_id, user_id, score (0–100), computed_at

- saved_spots — user_id, venue_id, saved_at, notes

- waitlist — email, city, created_at, converted

Phase 1 MVP Core · 4–5 Weeks The first version of Neyece a real user can actually use.

## Sprints

| Sprint | Name | Key Deliverables | AI Tool Tip |
| --- | --- | --- | --- |
| S1.1 | Auth + Onboarding Week 1–2 | - Clerk auth integrated (email + Google sign-in) - Vibe onboarding quiz (4 screens, 3–4 questions each) - Answers stored to vibe_profiles table as JSONB - City selection with launch city gating (NY, LA, Chicago, Miami) - Onboarding completion → redirects to discovery feed - Progress bar + back navigation | Feed Claude Code the quiz screen mockup HTML and ask it to generate the React component with state management and Supabase write. |
| S1.2 | Venue Database Seed Week 2 | - Google Places API integration for venue ingestion - Seed script: 500+ venues per launch city - Vibe tags manually curated for top 50 venues per city - Neighborhood taxonomy defined per city - Venue admin dashboard (internal, basic) - Image pipeline from Google Places → Supabase Storage | Ask Claude Code to write the Google Places ingestion script with rate limiting and deduplication built in. |
| S1.3 | Discovery Feed Week 3 | - Home screen with mood selector strip - Horizontal featured card scroll (top picks) - Vertical nearby gems list - Basic vibe matching: filter venues by mood + city - Venue card with name, neighborhood, distance, vibe tags - Neyece Score badge (placeholder score for now) | Prompt: "Build a Next.js discovery feed page with a horizontal scroll card section and a vertical list. Fetch from Supabase. Use Tailwind." |
| S1.4 | Venue Detail Screen Week 4 | - Full venue detail page with hero image - Vibe tags, hours, distance, insider tip - AI insight panel: "Why this is Neyece for you" (static template for now) - "That's Neyece" primary CTA button - Save to Saved Spots (heart button) - Share venue as card (image generation) | Use Claude Code to generate the share card as a Vercel OG image (Next.js built-in) with the coral + eye-gradient wordmark. |

## Phase 1 Exit Criteria

- A new user can sign up, complete onboarding, and see a personalized discovery feed

- At least 200 venues seeded per launch city with accurate vibe tags

- Venue detail page loads and displays correctly on mobile

- Save and share features work end-to-end

Phase 2 Intelligence · 3–4 Weeks The moat. This is what makes Neyece impossible to copy quickly.

## Sprints

| Sprint | Name | Key Deliverables | AI Tool Tip |
| --- | --- | --- | --- |
| S2.1 | Neyece Score Engine Week 1–2 | - Scoring algorithm: user vibe vector × venue vibe vector → 0–100 score - Vibe fingerprint stored as embedding (pgvector in Supabase) - Score computed on login + refreshed on vibe update - Scores cached per user-venue pair for performance - Feed re-sorted by Neyece Score (replaces distance-first) - Score badge updated from placeholder to real values | Ask Claude: "Design a cosine similarity scoring system between a user vibe vector and venue tag vectors in PostgreSQL with pgvector." |
| S2.2 | AI Insight Generation Week 2–3 | - Claude API integration (claude-sonnet-4-6) - "Why this is Neyece for you" — real AI-generated per user + venue - Prompt template: user profile + venue tags → 2-sentence personal insight - Insights cached in DB to avoid repeat API calls - Fallback to template if API fails - Tone: warm, friendly, like a knowledgeable local friend | Your system prompt: "You are a knowledgeable local friend who knows this person's taste. In 1-2 sentences, explain why this specific venue matches their vibe. Be warm and specific, never generic." |
| S2.3 | Vibe Learning Loop Week 3–4 | - Implicit signal tracking: saves, shares, detail views, time on page - Explicit signals: "That's Neyece" button = strong positive - Vibe profile updated weekly based on signal accumulation - Feed gets measurably more accurate with each interaction - User-facing: "Your taste profile" view showing vibe fingerprint - Re-onboarding prompt after 30 days of inactivity | Prompt Claude Code: "Build a signal tracking system that writes user interaction events to Supabase and runs a weekly cron job to update vibe_profiles." |

## The Neyece Score Formula

The score is a weighted combination of three signals:

- Vibe Match (50%) — cosine similarity between user fingerprint vector and venue tag vector

- Freshness Bonus (20%) — venues not yet visited by the user score higher

- Mood Alignment (20%) — current session mood matches venue primary vibe

- Social Signal (10%) — boosted by saves + "That's Neyece" clicks from similar users

Score range 85–100 = "For You Tonight" featured cards. 70–84 = Nearby Gems list. Below 70 = not surfaced unless no alternatives.

Phase 3 Social Layer · 3–4 Weeks Turn Neyece users into brand evangelists — built into the product.

## Sprints

| Sprint | Name | Key Deliverables | AI Tool Tip |
| --- | --- | --- | --- |
| S3.1 | User Profiles Week 1 | - Profile page: avatar, display name, city, vibe summary - Taste profile visualization (top vibes as colored tags) - Discovery stats: spots found, Neyece reactions given - Edit profile + update city - Public profile URL (optional, opt-in) | Prompt: "Build a user profile page in Next.js that reads from Supabase and displays vibe tags as colorful pill components." |
| S3.2 | Saved Spots Week 1–2 | - Saved Spots tab: all bookmarked venues in a grid - Collections: user-created lists ("Date Night," "Sunday Morning") - Notes per saved venue (private) - Sort by: recently saved, Neyece Score, neighborhood - Share a collection as a curated list (generates link) | Ask Claude Code to scaffold the collections feature with a many-to-many relationship in Supabase between users, collections, and venues. |
| S3.3 | Share System Week 2–3 | - "That's Neyece" share card: venue photo + score + user reaction - Dynamic OG image generation (Next.js + Vercel) - Pre-populated copy: "Just found this on Neyece. That's so Neyece." - Share to Instagram Stories (9:16), feed (1:1), and direct link - #SoNeyece hashtag embedded in all share content - Referral tracking: shares → signups → attribution | Use Next.js built-in OG image generation with @vercel/og. Ask Claude Code to build the card template matching the brand design. |
| S3.4 | Gamification Week 3–4 | - Neyece Streaks: consecutive weeks discovering new spots - Achievements: "First Neyece," "Scout" (10 saves), "Insider" (5 shares) - Scout tier system: Regular → Scout → Tastemaker → Legend - Streak counter on home screen header - Achievement unlock animation on screen | Keep gamification lightweight — Duolingo-style streak logic in a single Supabase function. Prompt Claude Code for the streak calculation cron. |

Phase 4 Launch · 2–3 Weeks Polish, test, onboard your waitlist, and go live.

## Sprints

| Sprint | Name | Key Deliverables | AI Tool Tip |
| --- | --- | --- | --- |
| S4.1 | QA + Performance Week 1 | - Full mobile QA on iOS Safari + Android Chrome - Core Web Vitals: LCP < 2.5s, CLS < 0.1 - Supabase RLS (Row Level Security) policies audited - API rate limiting on all endpoints - Error monitoring (Sentry) installed - GDPR-compliant privacy policy + data deletion flow | Prompt Claude: "Audit this Next.js app for performance bottlenecks, security gaps, and accessibility issues. Prioritize mobile." |
| S4.2 | Waitlist Onboarding Week 1–2 | - Invite email sequence (3 emails: invite → welcome → first discovery) - Batch onboard first 50 waitlist users by city - In-app feedback prompt after first 3 sessions - User interview scheduling (Calendly link in-app) - Dashboard tracking: DAU, saves, shares, "That's Neyece" clicks | Use Claude to write all 3 email templates in the Neyece voice — warm, playful, "cool friend" tone. Subject line: "Your city is waiting. That's Neyece." |
| S4.3 | Go Live Week 2–3 | - ProductHunt launch post drafted - Press outreach: local city guides + food/lifestyle press - #SoNeyece seed campaign with 20 micro-influencers - App Store submission (React Native wrapper or PWA) - City-by-city rollout: NYC first, then 1 new city per 2 weeks - Post-launch monitoring: error rates, drop-off points, feedback | Ask Claude to draft the ProductHunt tagline, first comment, and maker story. Keep the "That's Neyece" framing front and center. |

# Launch Success Metrics

| Success Metric | Target |
| --- | --- |
| Waitlist Signups (pre-launch) | 500+ emails |
| Day 1 Active Users | 100+ (first invite batch) |
| Onboarding Completion Rate | >70% |
| Week 1 Retention (D7) | >40% |
| "That's Neyece" button taps / DAU | >1.5 per active user |
| Share Rate | >15% of sessions result in a share |
| Organic #SoNeyece mentions | 50+ in first month |
| Venues per city (seeded) | 500+ with vibe tags |
| Average Neyece Score accuracy | >80% user-reported satisfaction |
| Referral Conversion | >25% of shares → signup |

# AI-Assisted Dev Workflow

This is how to move at solo-founder speed without burning out. Treat Claude Code and Cursor as your development team — you are the product lead and decision-maker.

| Task Type | How to Use AI | You Handle |
| --- | --- | --- |
| Scaffolding | Claude Code: "Build the full file structure for a Next.js feature: [name]. Include the route, component, API handler, and Supabase types." | Review + tweak naming, approve architecture |
| Component Build | Cursor: paste the HTML mockup, ask it to convert to React + Tailwind + Supabase data fetching | Brand decisions, edge cases, mobile behavior |
| Database | Claude Code: "Write the Supabase migration for [feature]. Include RLS policies and indexes." | Data model decisions, schema review |
| Algorithm | Claude: "Design a cosine similarity scoring algorithm for [use case] using pgvector." | Weighting decisions, business logic tuning |
| Copy + Voice | Claude: "Write this in the Neyece voice: warm, playful, like a cool local friend. Avoid corporate language." | Final approval, brand consistency |
| Debugging | Cursor: paste the error + relevant files. Ask for diagnosis + fix with explanation. | Understand the fix before applying it |
| Testing | Claude Code: "Write Jest tests for this function. Cover happy path, edge cases, and error states." | Define what matters to test |

"The best discovery app isn't the one with the most spots. It's the one that knows you." Neyece · That's Neyece.